## Overview
Test Case Overview
Project Name | Book Store Application
Current Version | 1.0
Project Code | BS-001
Issue Date | 2022-08-23
Recorded Change
Date | Version | Description | Issued by | Approved by | Further Notes
2022-08-23 | 1.0 | Test Case First Created | Boy Panji Lesmono | TBD

## Test Cases
Test Case
Project Name | Web Database
Pass | 14 | Pending | 0 | Positive Tests Conducted | 11
Fail | 2 | Test Cases Conducted | 16 | Negative Tests Conducted | 5
ID | Test Type | Test Case Description | Test Case Prerequisite | Test Case Procedure | Expected Result | Actual Result | Test Date | Status | Further Notes
Within the Book Store Application there exist function which users can register an account, login using existing account, browse(search and sort) books, add/remove book to/from their collection, log out, and delete account
Below is Test Cases Associated with the Register Page
TC01 | Negative | An user should not be able to register if they leave a field blank | User is viewing the Register Page | 1. Visit the register page 2. Fill the required fields except one 3. Check the Captcha 4. Press the Register Button | The user is prevented from registering and the blank field is highlighted | The user is prevented from registering and the blank field is highlighted | 2022-08-23 | Pass
TC02 | Negative | An user should not be able to register if they don't meet the password characters requirements | User is viewing the Register Page | 1. Visit the register page 2. Fill the required fields 3. Fill the password field as "12345678" 4. Check the Captcha 5. Press the Register Button | The user is prevented from registering and a warning message is displayed | The user is prevented from registering and a warning message is displayed | 2022-08-23 | Pass
TC03 | Negative | An user should not be able to register if they leave the Captcha unchecked | User is viewing the Register Page | 1. Visit the register page 2. Fill the required fields 3. Press the Register Button | The user is prevented from registering and a warning message is displayed | The user is prevented from registering and a warning message is displayed | 2022-08-23 | Pass
TC04 | Positive | An user should be able to register if they fill everything as it should | User is viewing the Register Page | 1. Visit the register page 2. Fill the required fields 3. Check the Captcha 4. Press the Register Button | The user is successfully registered and a notice is displayed | The user is successfully registered and a notice is displayed | 2022-08-23 | Pass
TC05 | Negative | An user should not be able to register if the user is already exist | User is viewing the Register Page | 1. Visit the register page 2. Fill the required fields using an used username 3. Check the Captcha 4. Press the Register Button | The user is prevented from registering and a warning message is displayed | The user is prevented from registering and a warning message is displayed | 2022-08-23 | Pass
Below is Test Cases Associated with the Login Page
TC06 | Negative | An user should not be able to login if they filled either the wrong user or password | User is viewing the Login Page | 1. Visit the login page 2. Fill nonexistent user or the wrong password 3. Click Login | The user failed to login and a warning message is displayed | The user failed to login and a warning message is displayed | 2022-08-23 | Pass
TC07 | Positive | An user should be able to login if they filled the correct username and password | User is viewing the Login Page | 1. Visit the login page 2. Fill the correct user and password 3. Click Login | The user successfully logged in | The user successfully logged in | 2022-08-23 | Pass
Below is Test Cases Associated with the Book Store Page
TC08 | Positive | A logged in user should be able to use the search button to search a specific book | User is logged in and is viewing the Book Store Page | 1. Visit the book store page 2. Type "Javascript" in the search field | All books displayed on the page now contains the phrase "Javascript" | All books displayed on the page now contains the phrase "Javascript" | 2022-08-23 | Pass
TC09 | Positive | A logged in user should be able to use the sort function to sort the books listed | User is logged in and is viewing the Book Store Page | 1. Visit the book store page 2. Click each of the column header | All books displayed on the page is now sorted properly | All books displayed on the page is now sorted properly, except for titles column which sorted randomly | 2022-08-23 | Fail | Upon deeper inspection the books are sorted through their ID instead of Titles when the header is clicked
TC10 | Positive | A logged in user should be able to add a book to their collection | User is logged in and is viewing the Book Store Page | 1. Visit the book store page 2. Click on the desired book 3. Click add to collection | A notice appears informing the book has been successfully added and is now can be viewed in Profile | A notice appears informing the book has been successfully added and is now can be viewed in Profile | 2022-08-23 | Pass
Below is Test Cases Associated with the Profile Page
TC11 | Positive | A logged in user should be able to use the search button to search a specific book | User is logged in and is viewing the Profile Page and has added few books added to their collection | 1. Visit the profile page 2. Type "Javascript" in the search field | All books displayed on the page now contains the phrase "Javascript" | All books displayed on the page now contains the phrase "Javascript" | 2022-08-23 | Pass
TC12 | Positive | A logged in user should be able to use the sort function to sort the books listed | User is logged in and is viewing the Profile Page and has added few books added to their collection | 1. Visit the profile page 2. Click each of the column header | All books displayed on the page is now sorted properly | All books displayed on the page is now sorted properly, except for titles column which sorted randomly | 2022-08-23 | Fail | Upon deeper inspection the books are sorted through their ID instead of Titles when the header is clicked
TC13 | Positive | A logged in user should be able to remove a book from their collection | User is logged in and is viewing the Profile Page and has added few books added to their collection | 1. Visit the profile page 2. Click on the delete book icon 3. Accept the confirmation prompt | A notice appears informing the book has been successfully deleted and is now removed from collection | A notice appears informing the book has been successfully deleted and is now removed from collection | 2022-08-23 | Pass
TC14 | Positive | A logged in user should be able to logout | User is logged in and is viewing the Profile Page | 1. Visit the profile page 2. Click on the log out button | The user successfully logged out and is redirected to log in page | The user successfully logged out and is redirected to log in page | 2022-08-23 | Pass
TC15 | Positive | A logged in user should be able to remove all book from their collection using the Delete All Book button | User is logged in and is viewing the Profile Page and has added few books added to their collection | 1. Visit the profile page 2. Click on the delete all book button 3. Accept the confirmation prompt | A notice appears informing all book has been successfully deleted and is now removed from collection | A notice appears informing all book has been successfully deleted and is now removed from collection | 2022-08-23 | Pass
TC16 | Positive | A logged in user should be able to delete their account | User is logged in and is viewing the Profile Page | 1. Visit the profile page 2. Click on the delete account button | A notice appears informing user is deleted and now is redirected to login page | A notice appears informing user is deleted and now is redirected to login page | 2022-08-23 | Pass

## Report
Test Report
Date | 2022-07-20
Further Notes | …
No | Project Name | Pass | Fail | Pending | Number of Test Conducted
1 | Book Store Application | 14 | 2 | 0 | 16
Sub Total |  | 14 | 2 | 0 | 16
Total | Percentage
Test Coverage | 100 | %
Success Coverage | 87.5 | %